## UX Task Tracker
StartPray UX Task Tracker (from TODO0314.MD)
Total Tasks
Completed Tasks
Overall Completion
Weighted Remaining Effort
Source document: TODO0314.MD (repository root)
ID | Task Description | Route | Priority | Est. Effort (%) | Status | Completion (%) | Remaining Effort (%) | Priority Weight | Weighted Remaining | Owner | Due Date | Source URL | Notes
UX-01 | 首屏主流程不清楚，使用者不知道第一步該做什麼 | `/prayfor` | P0 | 10% | Not Started | [6 empty] | https://startpray.online/prayfor | 問題已確認，待版型重排 ¦ 確定首屏只留 1 主 CTA + 1 次 CTA
UX-02 | 搜尋與卡片牆出現太晚，使用者要滑很久才進入主任務 | `/prayfor` | P0 | 10% | Not Started | [6 empty] | https://startpray.online/prayfor | 問題已確認，尚未改版 ¦ 將搜尋/熱門牆前移到 hero 後第一區塊
UX-03 | 登入/忘記密碼流程訊息矛盾，造成中斷感 | `/login` `/forgot-password` | P0 | 15% | Not Started | [6 empty] | https://startpray.online/prayfor | 問題已確認，流程未修正 ¦ 恢復 forgot-password 頁並更新登入頁文案
UX-04 | 詳情頁操作元素過多，主任務優先順序不清楚 | `/prayfor/[id]` | P0 | 10% | Not Started | [6 empty] | https://startpray.online/prayfor | 問題已確認，互動未收斂 ¦ 調整為「播放/回應/延伸瀏覽」三層 CTA
UX-05 | 手機版固定元件（header/播放器/浮動切換）互相搶空間 | `/prayfor` `/prayfor/[id]` | P1 | 10% | Not Started | [6 empty] | https://startpray.online/prayfor | 問題已確認，待行動版重排 ¦ 移除詳情頁浮動切換，播放器改 mini 模式
UX-06 | 後台手機版側欄與大表格可用性不足 | `/admin/*` | P1 | 10% | Not Started | [6 empty] | https://startpray.online/prayfor | 問題已確認，尚未實作 ¦ 補 mobile sidebar toggle 與表格行動版策略
UX-07 | 後台導覽與頁面真實性不一致（示意頁混在正式流程） | `/admin/*` | P0 | 20% | Not Started | [6 empty] | https://startpray.online/prayfor | 已盤點哪些頁為示意資料 ¦ 導覽拆分「正式可用 / 規劃中」
UX-08 | 後台操作回饋風格不一致（alert/confirm/inline 混用） | `/admin/*` | P1 | 10% | Not Started | [6 empty] | https://startpray.online/prayfor | 問題已確認 ¦ 定義統一 toast + confirm dialog 規範